## Dashboard
Installation POC Checklist Dashboard
Repo snapshot: main -> origin/main; pushed status is based on local git state checked 2026-06-09.
Executive Summary
Total Tasks |  |  | P0 Must Fix |  |  | Person A Tasks |  | Person B Tasks
| 53 |  |  | 28 |  |  | 17 |  | 19
Pushed Yes |  |  | Pushed Partial |  |  | Not Pushed |  | Deferred/N-A
| 0 |  |  | 8 |  |  | 38 |  | 7
Owner | P0 | P1 | P2 |  | Pushed Status | Count | Share
Shared | 10 | 0 | 0 |  | No | 38 | 71.7%
Person A | 9 | 8 | 0 |  | Partial | 8 | 15.09%
Person B | 9 | 10 | 0 |  | Yes | 0 | 0%
Optional | 0 | 0 | 7 |  | N/A | 7 | 13.21%
Decision Notes
1 | Role management and proper MRI/Cath separation are P0 and should be implemented before demo polish.
2 | KPI dashboard and monthly calendar are P1 because the latest request makes them expected demo items.
3 | Budget and full time-spent tracking remain P2 until Philips confirms they are required.
4 | The pushed-status column is editable; current values are based on the local git snapshot, not remote CI.

## Checklist
Installation POC Delivery Checklist
Corporate task tracker for Person A, Person B, shared foundation, git push status, and demo readiness.
Owner | Workstream | Priority | Task | Acceptance Criteria | Source | Implementation Status | Pushed to Git Repo? | Current Repo Evidence / Notes | Assigned To | Target
Shared | Foundation | P0 | Agree final field names and status constants | Common constants for profile types, statuses, roles, priorities, and document states are agreed and reused. | Section 5 - Shared Foundation | To Do | No | Current code uses scattered strings; needs shared constants. | Both | Sprint 1
Shared | Foundation | P0 | Align migrations with PRD names or document local names | Migrations either match the PRD vocabulary or local deviations are documented clearly. | Section 5 - Shared Foundation | Partial | Partial | Installation/profile migrations exist, but foreign keys and names are inconsistent. | Both | Sprint 1
Shared | Foundation | P0 | Decide how role is stored on users | A role field or equivalent internal mechanism exists for admin, biomedical, and optional manager. | Section 5 - Shared Foundation | To Do | No | No user role column, gate, policy, or middleware found. | Both | Sprint 1
Shared | Foundation | P0 | Define permission matrix and status transition matrix | The PRD permission matrix and state-machine transitions are encoded in a simple reference/service. | Section 5 - Shared Foundation | To Do | No | Routes are open resource routes; edit form allows any listed status. | Both | Sprint 1
Shared | Foundation | P0 | Fix seed and demo data | Seed data creates valid users, clients, equipment, MRI installation, Cath installation, documents, and statuses. | Section 5 - Shared Foundation | To Do | No | DummyDataSeeder is untracked and inconsistent with current equipment schema. | Both | Sprint 1
Shared | Foundation | P0 | Maintain shared demo script | Demo script covers create MRI, create Cath, attach equipment/document, transition status, show dashboard/calendar, and blocked action. | Section 5 - Shared Foundation | To Do | No | No runnable demo checklist/script in repo yet. | Both | Sprint 4
Shared | Integration | P0 | Ensure php artisan migrate:fresh --seed works | Fresh migration and seed run cleanly from zero database state. | Section 6 - Checkpoint 1 | To Do | No | Migration constraints and seed mismatch need cleanup before this can be trusted. | Both | Sprint 1
Shared | Integration | P0 | Add one-to-one profile constraints | Each installation has at most one matching MRI or Cath child profile. | Section 6 - Checkpoint 1 | Partial | Partial | MRI has constrained installation_id; Cath uses unsignedBigInteger and no uniqueness. | Both | Sprint 1
Shared | Integration | P0 | Create demo users with roles | Admin, biomedical, and optional manager demo accounts exist and are usable in tests/demo. | Section 6 - Checkpoint 1 | To Do | No | Users exist through factory only; roles are not defined. | Both | Sprint 1
Shared | Documentation | P0 | Document real, simulated, and deferred scope | Limitations around DMS, manager role, budget/time, interventions, and production integration are visible. | Section 3 - P0 Backlog | Partial | No | Local planning docs exist but are untracked, not pushed. | Both | Sprint 4
Person A | Roles and Permissions | P0 | Add simple role model | User model supports admin, biomedical, and optional manager role values. | Section 5 - Person A | To Do | No | No role field exists in users migration/model. | Person A | Sprint 1
Person A | Roles and Permissions | P0 | Add InstallationPolicy or middleware | Server-side authorization protects create, edit, archive, document, status, KPI, and calendar actions. | Section 4 - Role Management | To Do | No | No policies/gates/middleware found for module actions. | Person A | Sprint 1
Person A | Roles and Permissions | P0 | Implement admin vs biomedical vs manager checks | Admin has full access; biomedical can create/edit but not archive; manager is read-only unless enabled. | Section 4 - Permission Matrix | To Do | No | No role-specific checks currently enforced. | Person A | Sprint 1
Person A | Status Workflow | P0 | Implement status transition service | Allowed transitions are checked against role and minimum conditions before update. | Section 5 - Person A | To Do | No | Status update currently happens through generic edit validation. | Person A | Sprint 2
Person A | Status Workflow | P0 | Guard archive as admin-only | Biomedical and manager cannot archive/delete; attempted archive is rejected and visible in tests. | Section 5 - Person A | To Do | No | Destroy route is exposed through resource route. | Person A | Sprint 2
Person A | MRI Profile | P0 | Clean up MRI migration and model | MRI profile table/model use consistent naming, relationship, casts, and one-to-one constraints. | Section 5 - Person A | Partial | Partial | profil_irms migration/model exists but is not integrated in parent flow. | Person A | Sprint 2
Person A | MRI Profile | P0 | Add MRI validation rules | MRI required fields block validation/operational status when missing. | Section 5 - Person A | To Do | No | Installation request validates common fields only. | Person A | Sprint 2
Person A | MRI Profile | P0 | Add MRI fields to create/edit flow | Selecting IRM displays and saves MRI-specific fields in the parent installation form. | Section 5 - Person A | To Do | No | Create/edit views only expose common installation fields. | Person A | Sprint 2
Person A | MRI Profile | P0 | Display MRI tab on detail page | Detail page shows MRI profile values when installation type is IRM. | Section 5 - Person A | To Do | No | Show page loads/displays Cath profile only. | Person A | Sprint 2
Person A | MRI Profile | P1 | Define required documents for MRI | MRI document checklist includes installation report, reception report, room plan, prevention plan, and conformity certificate if applicable. | Section 5 - Person A | To Do | No | No required-document rules by profile exist. | Person A | Sprint 3
Person A | KPI Dashboard | P1 | Build KPI backend counts | Backend returns counts by profile, status, maintenance, missing main equipment, and missing blocking documents. | Section 5 - Person A | To Do | No | Root redirects to installations index; no dashboard controller found. | Person A | Sprint 3
Person A | KPI Dashboard | P1 | Create KPI dashboard view | Dashboard shows clean cards/charts for active installations, profile split, operational rate, and exceptions. | Section 5 - Person A | To Do | No | No dashboard view exists. | Person A | Sprint 3
Person A | Tests | P1 | Test biomedical can create and update MRI | Feature test proves biomedical role can complete MRI parent/profile flow. | Section 5 - Person A | To Do | No | Only starter example tests exist. | Person A | Sprint 4
Person A | Tests | P1 | Test manager cannot edit | Manager role can view where enabled but cannot edit common or profile fields. | Section 5 - Person A | To Do | No | No manager role or authorization tests exist. | Person A | Sprint 4
Person A | Tests | P1 | Test biomedical cannot archive | Feature test rejects archive by biomedical and permits archive by admin. | Section 5 - Person A | To Do | No | Destroy route currently has no role guard. | Person A | Sprint 4
Person A | Tests | P1 | Test invalid status transition is rejected | Direct jump or forbidden transition is blocked and not historized as valid. | Section 5 - Person A | To Do | No | No transition service or tests exist. | Person A | Sprint 4
Person A | Tests | P1 | Test dashboard numbers match seeded data | Dashboard KPI values match seeded demo dataset. | Section 5 - Person A | To Do | No | No dashboard or seeded KPI test data exists. | Person A | Sprint 4
Person B | Cath Profile | P0 | Clean up Cath migration and model | Cath profile uses foreign key, one-to-one uniqueness, casts, and relationship consistency. | Section 5 - Person B | Partial | Partial | ProfilCatLab model/controller exist; migration lacks constrained FK/unique constraint. | Person B | Sprint 2
Person B | Cath Profile | P0 | Add Cath validation rules | Cath required fields block validation/operational status when missing. | Section 5 - Person B | To Do | No | Cath controller validates profile only in separate route; parent flow ignores it. | Person B | Sprint 2
Person B | Cath Profile | P0 | Add Cath fields to create/edit flow | Selecting CATHETERISME displays and saves Cath-specific fields in the parent installation form. | Section 5 - Person B | To Do | No | Installation create/edit forms do not include Cath fields. | Person B | Sprint 2
Person B | Cath Profile | P0 | Display Cath tab on detail page | Detail page shows Cath profile values when installation type is CATHETERISME. | Section 5 - Person B | Partial | Partial | Show page displays Cath details if profile exists, but parent create/update does not create it. | Person B | Sprint 2
Person B | Cath Profile | P1 | Define required documents for Cath | Cath checklist includes reception report, quality control, radioprotection documents, prevention plan, and technical reports. | Section 5 - Person B | To Do | No | No required-document rules by profile exist. | Person B | Sprint 3
Person B | Documents | P0 | Add DMS-compatible document metadata fields | Document table supports DMS id, profile type, file/url fallback, active flag, uploader, and replacement link. | Section 5 - Person B | Partial | Partial | Document table/controller exist but only category/version/status/blocking fields are stored. | Person B | Sprint 2
Person B | Documents | P1 | Enforce active version rule for blocking docs | Only one active version exists per blocking document category/profile/installation. | Section 5 - Person B | To Do | No | No active-version concept exists. | Person B | Sprint 3
Person B | Documents | P0 | Improve document status display | Detail page and document list show document category, version, status, blocking flag, and DMS/file reference. | Section 5 - Person B | Partial | Partial | Current display shows category/version/status/blocking but no DMS/file reference. | Person B | Sprint 2
Person B | Documents | P1 | Add missing required-document detection | List/detail/dashboard can flag installations missing required blocking documents. | Section 5 - Person B | To Do | No | No missing-document logic exists. | Person B | Sprint 3
Person B | Equipment Links | P0 | Display main equipment by relation | Detail/list show equipment code and designation, not only raw equipment_principal_id. | Section 5 - Person B | To Do | No | Detail page displays raw equipment principal ID. | Person B | Sprint 2
Person B | Equipment Links | P0 | Constrain secondary equipment pivot | Pivot has foreign keys, no duplicate installation/equipment pair, and clear role values. | Section 5 - Person B | Partial | Partial | Pivot table exists but lacks explicit constraints. | Person B | Sprint 2
Person B | Equipment Links | P0 | Show sub-equipment through linked equipment | Sub-equipment remains sourced from existing equipment relation and is visible from installation detail. | Section 5 - Person B | To Do | No | Installation detail lists linked equipment only, not sub-equipment through equipment. | Person B | Sprint 3
Person B | Calendar | P1 | Add installation planning dates | Installation stores planned and optional actual start/end dates for calendar tracking. | Section 5 - Person B | To Do | No | Installations table has no planning date fields. | Person B | Sprint 3
Person B | Calendar | P1 | Build calendar controller query by month | Calendar route returns installations planned for selected month with previous/next navigation. | Section 5 - Person B | To Do | No | No calendar route/controller found. | Person B | Sprint 3
Person B | Calendar | P1 | Create monthly calendar or grouped-list view | Corporate internal calendar view shows code, name, profile, status, client/site for selected month. | Section 5 - Person B | To Do | No | No calendar view exists. | Person B | Sprint 3
Person B | Tests | P1 | Test Cath installation saves child profile | Feature test proves parent create/update saves Cath child profile. | Section 5 - Person B | To Do | No | No Cath profile feature tests exist. | Person B | Sprint 4
Person B | Tests | P1 | Test wrong profile child cannot be attached | Cath data cannot attach to MRI installation and MRI data cannot attach to Cath installation. | Section 5 - Person B | To Do | No | No profile mismatch guard exists. | Person B | Sprint 4
Person B | Tests | P1 | Test document attach/blocking/missing logic | Tests cover document attachment, blocking flag, active version, and missing required document status. | Section 5 - Person B | To Do | No | No document workflow tests exist. | Person B | Sprint 4
Person B | Tests | P1 | Test calendar selected month | Calendar only shows installations planned in the requested month. | Section 5 - Person B | To Do | No | No calendar feature exists. | Person B | Sprint 4
Optional | Future Scope | P2 | Manager validation workflow | Manager validation remains disabled unless Philips confirms activation. | Section 3 - P2 Backlog | Deferred | N/A | PRD marks manager optional; do not block POC on this. | Person A | Optional
Optional | Future Scope | P2 | Export CSV or Excel | Filtered installation list can export if time allows. | Section 3 - P2 Backlog | Deferred | N/A | Should not outrank profile, roles, documents, dashboard, or calendar. | Shared | Optional
Optional | Budget and Time | P2 | Add optional budget fields if confirmed | budget_prevu, budget_reel, and devise are added only after stakeholder confirmation. | Section 7 - Budget and Time | Deferred | N/A | Current PRD/scope/tables do not require financial budget. | Shared | Optional
Optional | Budget and Time | P2 | Add optional time/duration fields if confirmed | temps_prevu_heures, temps_reel_heures, planned dates, and actual dates are added only as confirmed scope. | Section 7 - Budget and Time | Deferred | N/A | Calendar needs planning dates; full effort tracking is optional. | Shared | Optional
Optional | Documents | P2 | Full DMS versioning integration | Use real DMS versioning if structure is confirmed and quickly exploitable. | Section 3 - P2 Backlog | Deferred | N/A | POC table fallback is acceptable. | Person B | Optional
Optional | Audit | P2 | Audit log beyond status/document events | Critical field changes, validation, replacement, and archive events are logged in a dedicated audit table if time allows. | Section 3 - P2 Backlog | Deferred | N/A | Status history exists partially; full audit is future scope. | Shared | Optional
Optional | Interventions | P2 | Integrate intervention table if found | Open interventions can contribute to maintenance KPI if existing table is identified. | Section 3 - P2 Backlog | Deferred | N/A | PRD lists intervention table as an open question. | Shared | Optional

## Permissions
POC Permission Matrix
Minimal internal roles from the PRD and backlog. Manager remains optional/read-only by default.
Action | Admin | Biomedical | Manager Optional | Implementation Note
View list/detail | Yes | Yes | Yes | All internal users can view if authenticated.
View KPIs/calendar | Yes | Yes | Yes if enabled | Manager only if Philips activates the role.
Create installation | Yes | Yes | No | Person A owns policy/middleware.
Edit common fields | Yes | Yes | No | Guard in update action and UI.
Edit profile fields | Yes | Yes | No | Applies to MRI and Cath child profiles.
Link equipment | Yes | Yes | No | Person B owns relation display and constraints.
Attach/replace document | Yes | Yes | No | Person B owns DMS fallback metadata.
Operational status changes | Yes | Yes | Validation only if enabled | Transition service owned by Person A.
Archive installation | Yes | No | No | Admin-only.
Manage users/roles | Yes | No | No | Keep simple for POC.

## Git Snapshot
Git Snapshot for Checklist Push Column
Used to initialize the 'Pushed to Git Repo?' field. Update this sheet after each push.
Checked At | 2026-06-09
Current Branch | main
Upstream | origin/main
Remote | https://github.com/ghaythmabrouk240-oss/extention_instalation.git
Status Summary | Local workspace has uncommitted changes; no pushed implementation detected for the new checklist tasks.
Interpretation | Rows marked Partial have baseline code present, but the requested checklist change is not fully pushed/completed.

## Lists
Implementation Status | Pushed Status | Priority | Owner
To Do | No | P0 | Shared
In Progress | Partial | P1 | Person A
Partial | Yes | P2 | Person B
Blocked | N/A |  | Optional
Done |  |  | Both
Deferred
Not Applicable