## Checklist
Installation POC - Person A / Person B Checklist
Simplified delivery tracker with clear task ownership, current status, and pushed-to-git visibility.
Total Tasks | P0 Must Fix | Person A | Person B | Not Pushed
27 | 15 | 7 | 8 | 22
Git note: main -> origin/main. No checklist implementation changes are confirmed as pushed. Local workspace still has uncommitted files.
Owner | Priority | Workstream | Task | Deliverable / Done When | Status | Pushed? | Next Step / Evidence
Shared | P0 | Foundation | Finalize naming and constants | Common names for profile types, statuses, roles, priorities, document states, and planning dates are agreed and reused. | To Do | No | Create shared constants/config before feature work continues.
Shared | P0 | Schema | Clean migrations and constraints | Migrations use consistent foreign keys, one-to-one profile constraints, and no orphan rows for profiles/documents/status/equipment links. | Partial | No | Some tables exist, but Cath/documents/status/pivot constraints need cleanup.
Shared | P0 | Permissions | Define roles and status matrix | Admin, biomedical, and optional manager permissions are written and mapped to allowed status transitions. | To Do | No | Use the PRD matrix; keep manager read-only/disabled unless confirmed.
Shared | P0 | Demo Data | Fix seed data | Seed creates valid demo users, clients, equipment, one MRI installation, one Cath installation, documents, and status history. | To Do | No | Current DummyDataSeeder is not reliable against the equipment schema.
Shared | P0 | Installation List | Add simple filters | List supports basic filtering by profile, status, client/site, main equipment, and missing documents when available. | To Do | No | Index currently loads all installations without filters.
Shared | P0 | Integration | Validate vertical slice | Fresh migration/seed works and both MRI and Cath installations can be created, viewed, edited, and historized. | To Do | No | Run after schema/profile/seed cleanup.
Shared | P0 | Documentation | Prepare demo script and limitations note | Demo script shows MRI, Cath, equipment, document, status, dashboard, calendar, and blocked unauthorized action. | Partial | No | Planning document exists locally, but implementation/demo artifacts are not pushed.
Person A | P0 | Roles | Implement role storage and authorization | Users have simple roles and server-side policy/middleware guards protect module actions. | To Do | No | Add user role field and InstallationPolicy or equivalent middleware.
Person A | P0 | Status Workflow | Implement transition service | Invalid status jumps are rejected, allowed transitions are historized, and archive is admin-only. | To Do | No | Current edit form allows broad status selection.
Person A | P0 | MRI Profile | Clean MRI model and schema | MRI profile has relationship, casts, validation-ready fields, and one-to-one integrity with Installation. | Partial | No | MRI model/table exist but are not fully integrated.
Person A | P0 | MRI Profile | Integrate MRI in create/edit/show | Selecting IRM displays/saves MRI-specific fields and detail page shows MRI profile values. | To Do | No | Installation forms currently save common fields only; show page loads Cath profile only.
Person A | P1 | MRI Documents | Define MRI required documents | MRI checklist tracks required installation/reception/room/prevention/conformity documents. | To Do | No | Needed for missing-document KPI and operational readiness.
Person A | P1 | Dashboard | Build KPI dashboard | Dashboard shows profile split, status counts, operational rate, maintenance count, missing equipment, missing blocking docs, and planned-this-month count. | To Do | No | Root route currently redirects to installation list.
Person A | P1 | Tests | Add Person A feature tests | Tests cover biomedical MRI create/update, manager cannot edit, biomedical cannot archive, invalid transition, and KPI counts. | To Do | No | Only starter tests are present.
Person B | P0 | Cath Profile | Clean Cath model and schema | Cath profile has relationship, casts, constrained foreign key, and one-to-one integrity with Installation. | Partial | No | Cath controller/model exist, but migration lacks strong constraints.
Person B | P0 | Cath Profile | Integrate Cath in create/edit/show | Selecting CATHETERISME displays/saves Cath-specific fields and detail page shows Cath profile values. | Partial | No | Show page can display Cath if present; parent flow does not create/update it.
Person B | P1 | Cath Documents | Define Cath required documents | Cath checklist tracks reception, quality control, radioprotection, prevention, and technical report documents. | To Do | No | Needed for missing-document logic.
Person B | P0 | Documents | Implement document attachment POC | Document table supports category, version, status, blocking flag, DMS object id or file/url fallback, active flag, uploader, and replacement link. | Partial | No | Current table stores only basic metadata.
Person B | P1 | Documents | Add active version and missing-doc rules | Only one active blocking version per type is allowed and missing required documents are visible. | To Do | No | No active-version or missing-document logic exists.
Person B | P0 | Equipment | Improve equipment and sub-equipment display | Main equipment is shown by relation, secondary equipment pivot is constrained, and sub-equipment is visible through linked equipment. | Partial | No | Main equipment currently appears mostly as raw ID; pivot lacks constraints.
Person B | P1 | Calendar | Build monthly installation calendar | Installation planning dates exist and a monthly view shows code, name, profile, status, and client/site. | To Do | No | No installation-level planning dates or calendar view exist.
Person B | P1 | Tests | Add Person B feature tests | Tests cover Cath child save, wrong-profile guard, document attach/blocking/missing logic, and calendar month filtering. | To Do | No | No feature tests for these flows exist.
Optional | P2 | Manager | Manager validation workflow | Manager approval remains disabled unless Philips confirms activation. | Deferred | N/A | Do not block POC delivery.
Optional | P2 | Export | Export filtered list | CSV/Excel export is added only after P0/P1 demo scope is stable. | Deferred | N/A | Could be useful, but not central.
Optional | P2 | Budget | Budget fields if confirmed | Add budget_prevu, budget_reel, and devise only if stakeholders request financial tracking. | Deferred | N/A | PRD and scope do not make budget mandatory.
Optional | P2 | Time Tracking | Time and effort fields if confirmed | Add planned/actual effort fields only if stakeholders request installation duration tracking. | Deferred | N/A | Calendar needs dates; full effort tracking is optional.
Optional | P2 | DMS/Audit | Full DMS, audit, and intervention integration | Real DMS versioning, audit logs, and intervention linkage are added only if existing tables are confirmed. | Deferred | N/A | Use POC fallback first.

## Reference
Reference - Permissions and Git Interpretation
Short reference used by the simplified checklist.
Action | Admin | Biomedical | Manager Optional | Owner | Note
View list/detail | Yes | Yes | Yes | Shared | Internal only.
Create/edit installation | Yes | Yes | No | Person A | Protected by policy/middleware.
Edit MRI profile | Yes | Yes | No | Person A | Profile-specific ownership.
Edit Cath profile | Yes | Yes | No | Person B | Profile-specific ownership.
Attach documents | Yes | Yes | No | Person B | DMS fallback accepted for POC.
Change operational status | Yes | Yes | Validation only if enabled | Person A | Transition service required.
Archive | Yes | No | No | Person A | Admin-only.
View KPIs/calendar | Yes | Yes | Yes if enabled | Shared | Dashboard and calendar are expected demo items.
Git Interpretation
Checked At | 2026-06-09
Branch | main
Upstream | origin/main
Remote | https://github.com/ghaythmabrouk240-oss/extention_instalation.git
Pushed? | No = not confirmed pushed; Yes = pushed to remote; N/A = optional/deferred or not a code change.